## Sprint 1 Daily SCRUM Standup
Question | Team Member | Week: xx/xx/202x-xx/xx/202x | [6 empty] | Week: xx/xx/202x-xx/xx/202x
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
What did you do yesterday? | Courtney Wilson |  | Team Charter | Research Company | Use Cases | Use Cases |  |  | Use Cases | Use Cases | level One Diagram | level One Diagram | Presentation
| Lupe Perez |  | Get in Contact with Sponser | Get in Contact with Sponser | Get question for form | Get question for form |  |  | Get question for form | Why we choose the project | Update Sponsor | Update Sponsor | Presentation
| Kayla Vincent |  | Research Company | Research Company | work on company background | work on company background |  |  | work on company background | Work On Envirorment | Work On Envirorment | Work On Envirorment | Presentation
| Christian Martinez |  | Research Company | Research Company | Work on Project objective | Work on deveribles and constraints |  |  | Work on deveribles and constraints | PSPI | PSPI | PSPI | Presentation
What will you work on today? | Courtney Wilson | Team Charter | Research Company | Use Cases | Use Cases | Use Cases |  |  | Use Cases | level One Diagram | level One Diagram | Presentation | Presentation
| Lupe Perez | Get in Contact with Sponser | Get in Contact with Sponser | Get question for form | Get question for form | Get question for form |  |  | Why we choose the project | Update Sponsor | Update Sponsor | Presentation | Presentation
| Kayla Vincent | Research Company | Research Company | work on company background | work on company background | work on company background |  |  | Work On Envirorment | Work On Envirorment | Work On Envirorment | Presentation | Presentation
| Christian Martinez | Research Company | Research Company | Work on Project objective | Work on deveribles and constraints | Work on deveribles and constraints |  |  | PSPI | PSPI | PSPI | Presentation | Presentation
Do you have any obstacles? | Courtney Wilson
| Lupe Perez |  | Having trouble communicating with sponser | Having trouble communicating with sponser
Kayla Vincent
Christian Martinez

## Sprint 2 Daily SCRUM Standup
Question | Team Member | Week: xx/xx/202x-xx/xx/202x | [6 empty] | Week: xx/xx/202x-xx/xx/202x
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
What did you do yesterday?
What will you work on today?
Do you have any obstacles?

## Sprint 3 Daily SCRUM Standup
Question | Team Member | Week: xx/xx/202x-xx/xx/202x | [6 empty] | Week: xx/xx/202x-xx/xx/202x | [6 empty] | Week: xx/xx/202x-xx/xx/202x
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
What did you do yesterday?
What will you work on today?
Do you have any obstacles?

## Sprint 4 Daily SCRUM Standup
Question | Team Member | Week: xx/xx/202x-xx/xx/202x | [6 empty] | Week: xx/xx/202x-xx/xx/202x | [6 empty] | Week: xx/xx/202x-xx/xx/202x
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
What did you do yesterday?
What will you work on today?
Do you have any obstacles?

## Sprint 5 Daily SCRUM Standup
Question | Team Member | Week: xx/xx/202x-xx/xx/202x | [6 empty] | Week: xx/xx/202x-xx/xx/202x
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
What did you do yesterday?
What will you work on today?
Do you have any obstacles?

## Sprint 6 Daily SCRUM Standup
Question | Team Member | Week: xx/xx/202x-xx/xx/202x | [6 empty] | Week: xx/xx/202x-xx/xx/202x
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
What did you do yesterday?
What will you work on today?
Do you have any obstacles?