## Sprint 1 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
1 | History and business description | 1 | [14 empty] | Kayla | 8 | bar: Day 1
2 | Description of current Enviroment | 1 | [14 empty] | Courtney | 11 | bar: Day 5
3 | Why chose this project | 1 | [14 empty] | Lupe | 9 | bar: Day 3
4 | Current Systems problems | 1 | [14 empty] | Christian | 11 | bar: Day 2
5 | Objective, Specifications and Constrants | 2 | [15 empty] | 39 | Total Team Time | bar: Day 3 to Day 4
6 | PSPI 1.0 | 4 | Day 7: 3; Day 9: 1
7 | Expected Benefits | 1 | bar: Day 5
8 | Problem Analyize | 1 | bar: Day 1
9 | Initial Context Diagram | 3 | Day 10: 1; Day 11: 2
10 | Initial Use Case Diagram | 2 | Day 4: 2
11 | level 1 diagram | 2 | bar: Day 8 to Day 9
| Meeting | 8 | Day 6: 4; Day 12: 4
| presentation | 8 | Day 13: 4; Day 14: 4
| Sponser Contact | 3 | bar: Day 3; Day 5; Day 10
Remaining Effort |  | 38 | 36 | 35 | 32 | 29 | 26 | 22 | 19 | 18 | 16 | 14 | 12 | 8 | 4 | 0
Ideal Effort |  | 38 | 35.2857 | 32.5714 | 29.8571 | 27.1429 | 24.4286 | 21.7143 | 19 | 16.2857 | 13.5714 | 10.8571 | 8.1429 | 5.4286 | 2.7143 | -1.1546e-14

## Sprint 2 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
Kayla
Courtney
Lupe
Christian
[18 empty] | 0 | Total Team Time
Remaining Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 3 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Team Member | Total Time
Kayla
Courtney
Lupe
Christian
[25 empty] | 0 | Total Team Time
Remaining Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 4 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Team Member | Total Time
Kayla
Courtney
Lupe
Christian
[25 empty] | 0 | Total Team Time
Remaining Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 5 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
Kayla
Courtney
Lupe
Christian
[18 empty] | 0 | Total Team Time
Remaining Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 6 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
Kayla
Courtney
Lupe
Christian
[18 empty] | 0 | Total Team Time
Total Project Time
[18 empty] | Sprint 1 | 39
[18 empty] | Sprint 2 | 0
[18 empty] | Sprint 3 | 0
[18 empty] | Sprint 4 | 0
[18 empty] | Sprint 5 | 0
[18 empty] | Sprint 6 | 0
[19 empty] | 39 | Total Project Time
Remaining Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0